## Project schedule
| Battery Packs project | [6 empty] | Project start: | [7 empty] | 2026-06-12
| DLOK NETWORKS PVT. LTD | [6 empty] | Display week: | [7 empty] | 8
[8 empty] | 2026-07-27 | [6 empty] | 2026-08-03 | [6 empty] | 2026-08-10 | [6 empty] | 2026-08-17 | [6 empty] | 2026-08-24 | [6 empty] | 2026-08-31 | [6 empty] | 2026-09-07 | [6 empty] | 2026-09-14
| TASK | ASSIGNED TO | PROGRESS | START | END | REMARK | time axis 2026-07-27 to 2026-09-20
 | time axis 2026-07-27 to 2026-09-20
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Phase 1: Sourcing, Cost Analysis & Benchmarking
| BOM & Raw Material Listing | Ayushman Sahoo | 100% | 2026-06-12 | 2026-06-12 | Initial component and specification list completed. | 1
| Street Light Battery Audit & Teardown | Ayushman Sahoo | 100% | 2026-06-16 | 2026-06-16 | Discovered specification discrepancy (labeled 24Ah vs. 18Ah actual capacity). | 1
| Vendor Negotitation & Cost Estimation | Ayushman Sahoo | 100% | 2026-06-13 | 2026-07-08 | Price fluctuations, component stockouts across 12–15 suppliers, and deferred management sign-off. | 26
| Procurement & Payment Processing | Ayushman Sahoo | 100% | 2026-07-09 | 2026-07-15 | Internal fund disbursement lead-time and executive sign-off availability. | 7
| Material Delivery & Lab Space Setup | Ayushman Sahoo | 100% | 2026-07-15 | 2026-07-27 | Supplier logistics lead-time and delayed workshop/lab space allocation. | 13
Phase 2: Project 1 — 16S 35Ah NMC Battery Pack Build
| 3D CAD Modeling of Battery Pack | Ayushman Sahoo | 100% | 2026-07-19 | 2026-07-21 | Cell layout and pack dimensioning completed on schedule. | 3
| Cell Holder Structural Fabrication | Ayushman Sahoo | 100% | 2026-07-22 | 2026-07-22 | Frame grid assembly completed. | 1
| Module 1 Spot Welding (16S Matrix) | Ayushman Sahoo | 100% | 2026-07-28 | 2026-07-28 | Primary nickel strip interconnect welding completed. | 1
| Module 2 Welding & BMS Wiring | Ayushman Sahoo | 100% | 2026-07-29 | 2026-07-29 | Secondary stack welding and BMS balance harness soldered. | 1
| Fiber Insulation & Heat-Shrink Wrap | Ayushman Sahoo | 100% | 2026-07-30 | 2026-07-30 | Primary electrical safety barrier and thermal wrap completed.
| Enclosure Dimensional Benchmarking | Ayushman Sahoo | 100% | 2026-07-31 | 2026-07-31 | Physical measurements completed for outer housing.
| Outer Metal Box CAD Design | Ayushman Sahoo | 100% | 2026-08-02 | 2026-08-03 | Metal housing blueprints finalized for fabrication.
| Connector Assembly & Bench Test | Ayushman Sahoo | 100% | 2026-08-04 | 2026-08-04 | High-current power connectors wired; initial vehicle bench test passed.
| Outer Metal Box Fabrication | Gobardhan Bhai | 100% | 2026-08-03 | 2026-08-07 | Workshop technician bandwidth constraints due to parallel tasks. | 5
| Vehicle Installation & Charging | Ayushman Sahoo | 100% | 2026-08-08 | 2026-08-08 | Installed in vehicle and charged to full 67.2V capacity.
| Road Endurance & Range Test (100–0%) | Ayushman Sahoo | 100% | 2026-08-09 | 2026-08-14 | Successfully validated 85.8 km total range with 641m elevation gain.
Phase 3: Project 2 — Solar Street Light Battery Development
| Secondary Fixture Power Audit | Ayushman Sahoo | 100% | 2026-08-11 | 2026-08-11 | Identified driver power scaling (16.6W actual vs. 45W advertised rating). | 1
| Solar Light Sourcing & Quotations | Ayushman Sahoo | 100% | 2026-08-11 | 2026-08-13 | Evaluated 6 wholesale suppliers for semi-integrated fixture components. | 3
| Material Order for Solar Pack | Ayushman Sahoo | 100% | 2026-08-13 | 2026-08-13 | Procurement purchase order submitted to vendor. | 1
| In-Transit Material Shipment Lead Time | Ayushman Sahoo | 100% | 2026-08-13 | 2026-08-25 | Supplier transit lead-time; delivery expected on or before Aug 25. | 13
| Cell Inspection & Quality Audit | Ayushman Sahoo | 100% | 2026-08-26 | 2026-08-26 | Inspected physical cell integrity, baseline voltages, and internal resistance. | 1
| Cell Grouping & 6P Sub-Pack Spot Welding | Ayushman Sahoo | 100% | 2026-09-07 | 2026-09-07 | Matched cell capacities and spot-welded four parallel 6P sub-pack modules.
| 4S Series Welding, BMS Wiring & Heat Shrink | Ayushman Sahoo | 100% | 2026-09-10 | 2026-09-10 | Welded 4S series connections, wired TDT BMS & power leads, and completed PVC heat shrink wrap.
Evaluation
|  | Ayushman Sahoo | 25%
|  | Ayushman Sahoo | 25%
|  | Ayushman Sahoo | 50%
|  | Ayushman Sahoo | 60%
|  | Ayushman Sahoo | 50%
Insert new rows ABOVE this one

## About
SIMPLE GANTT CHART by Vertex42.com
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.